## Worksheet
Date | Task | Time Spent (Hours) |  |  | Status
|  | Planned | Actual | Variance
2024-04-01 | Project Planning Meeting | 1.5 | 1.5 | 0 | Completed
2024-04-03 | Design Mockups | 3 | 2.5 | -0.5 | In Progress
2024-04-05 | Code Development | 5 | 4.8 | -0.2 | In Progress
2024-04-07 | Unit Testing | 2 | 2 | 0 | Completed
2024-04-10 | Client Review Meeting | 1.5 | 1.5 | 0 | Completed
2024-04-12 | Documentation Update | 2.5 | 3 | 0.5 | Completed
2024-04-15 | Final Review & Approval | 3 | 3 | 0 | Completed
Total Planned: |  |  | 20 | Total Actual: | 19.8 | Overall Variance: -0.2h