## Worksheet
Task | Assigned To | Due Date | Priority | Status | Progress (%) | Notes
Complete Q3 Financial Report | Sarah Johnson | 2023-10-15 | High | In Progress | 65% | Data validation pending from sales team.
Conduct Customer Satisfaction Survey | Mike Chen | 2023-10-20 | Medium | Not Started | 0% | Survey tool to be distributed via email.
Review and Approve Product Launch Plan | Linda Patel | 2023-11-01 | High | Pending Review | 40% | Marketing materials in draft phase.
Schedule Quarterly Team Meeting | David Ruiz | 2023-10-18 | Low | Completed | 100% | Meeting held on Oct 16, attendees all present.
Update Performance KPI Dashboard | Anna Kim | 2023-11-10 | High | Not Started | 0% | Needs integration with new CRM data.