## Worksheet
Week | Project Name | Budgeted Amount ($) | Actual Spend ($) | Variance ($) | % of Budget | Status | Notes
Week 1 | Product Launch Campaign | 15000 | 14200 | 800 | 94.7% | On Track | Ad spend below target; early content delivery.
Week 2 | Website Redesign | 20000 | 19500 | <+500 | 97.5% | On Track | Development completed on schedule.
Week 3 | Customer Support Upgrade | 8000 | 8400 | -400 |  | 105.0% | Over Budget | Unplanned training costs increased expenses.
Week 4 | Marketing Analytics Tools | 12000 | 11800 | 200 | 98.3% | On Track | All data integration successful.
Week 5 | Staff Training Program | 6000 | 6300 | -300 | 105.0% | Over Budget | Add-on sessions required due to high demand.