## Worksheet
Week | Date Range | Key Objective | Tasks & Actions | Progress (✅/❌) | Owner | Notes / Observations
Week 1 | Mon, Jan 6 – Sun, Jan 12 | Establish baseline KPIs and team performance metrics | Conduct team interviews Review past quarterly reports Define measurement criteria | ✅ | Sarah Thompson | All KPIs aligned with company goals. Team feedback was positive.
Week 2 | Mon, Jan 13 – Sun, Jan 19 | Launch performance tracking system for team | Set up dashboards Train department leads Distribute access credentials | ✅ | Michael Chen | All departments completed initial training. Feedback form shows 93% satisfaction.
Week 3 | Mon, Jan 20 – Sun, Jan 26 | Review performance data and adjust goals | Run weekly performance reports Identify underperforming areas Adjust KPI targets | ❌ | Lisa Wong | Data collection delayed due to system outage. Rescheduled for next week.
Week 4 | Mon, Jan 27 – Sun, Feb 2 | Conduct team performance review meeting | Schedule one-on-ones Document feedback Plan development goals | ✅ | David Kim | All team members participated. Goals are now actionable and time-bound.
Week 5 | Mon, Feb 3 – Sun, Feb 9 | Monitor progress and report to leadership | Compile performance summary Submit weekly report to executive team Highlight key achievements | ✅ | Sarah Thompson | Leadership approved new strategy based on performance insights.