## Worksheet
Week | Date Range | Key Goals | Actions Taken | Progress (✔/✘) | Blocked Issues | Next Steps | Owner
1 | Mon, Apr 8 – Sun, Apr 14 | Launch MVP prototype | Completed UI mockups and user flow design | ✔ | Design feedback from stakeholders delayed | Reschedule stakeholder review for Thursday, Apr 10 | Alex Chen
2 | Mon, Apr 15 – Sun, Apr 21 | Integrate API with backend | Connected payment gateway and authentication | ✔ | API rate limits causing delays in testing | Optimize request batching to reduce calls | Samira Patel
3 | Mon, Apr 22 – Sun, Apr 28 | User onboarding flow testing | Conducted A/B test with new onboarding funnel | ✔ | Low completion rate in step three | Simplify step-by-step instructions and add tooltips | Jordan Lee
4 | Mon, Apr 29 – Sun, May 5 | Finalize product documentation | Updated developer guide and admin setup docs | ✔ | Missing integration examples for new modules | Add sample code snippets in next sprint | Taylor Reed