## Worksheet
Week | Team Member | Objective | Progress (1-5) | Key Achievements | Challenges Faced | Action Items | Next Steps
Week 1 | John Doe | Complete project kickoff meeting and finalize scope. | 4 | Completed all team alignment sessions; documented scope document. | Limited input from UX team early on. | Schedule follow-up with UX lead. | Finalize project timeline by Friday.
Week 2 | Jane Smith | Develop prototype for user onboarding flow. | 3 | Created initial wireframes; gathered feedback from 3 users. | Time constraints during sprint planning. | Revise prototype based on user feedback. | Present updated prototype to stakeholders by Thursday.
Week 3 | Alex Turner | Conduct sprint planning and assign tasks. | 5 | All tasks clearly defined; team agreed on priorities. | None reported. | None required. | Ensure daily stand-ups are scheduled and tracked.
Week 4 | Mia Johnson | Complete QA testing of core features. | <4 | Discovered 3 critical bugs; reported to dev team. | Some feature inconsistencies across devices. | Coordinate with developers to fix bugs by end of week. | Prepare summary report for next review meeting.