## Worksheet
Week | Date Range | Objective | Key Activities | Progress (%) | Issues/Challenges | Next Steps | Responsible Person
Week 1 | Mon, Jan 6 – Sun, Jan 12 | Launch project kickoff meeting | Team alignment; goal setting; resource mapping | 85% | Limited participation from remote team members | Schedule follow-up call with remote staff | Sarah Johnson
Week 2 | Mon, Jan 13 – Sun, Jan 19 | Complete initial market research | Surveys; data collection; analysis of competitors | 90% | Delayed response from external vendors | Follow up with vendors to expedite responses | Michael Chen
Week 3 | Mon, Jan 20 – Sun, Jan 26 | Develop prototype for product feature | UI/UX design; user feedback sessions; wireframing | 75% | Design inconsistency in early drafts | Revisit design standards with cross-functional team | Lisa Rodriguez
Week 4 | Mon, Jan 27 – Sun, Feb 2 | Finalize product roadmap | Stakeholder review; timeline validation; budget assessment | 80% | Lack of clear priority from leadership | Present updated roadmap with clear priorities to leadership | David Kim
Week 5 | Mon, Feb 3 – Sun, Feb 9 | Begin beta testing phase | Recruit test users; deploy early version; collect feedback | 60% | Low user engagement in first session | Adjust onboarding process and send reminder emails | Emma Thompson