## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | 100 | Sarah Johnson
Needs Assessment | 2024-03-06 | 2024-03-15 | 10 | 85 | Mark Taylor
Plan Development | 2024-03-16 | 2024-04-05 | 21 | 60 | Lisa Chen
Team Training | 2024-04-06 | 2024-04-12 | 7 | 95 | David Kim
Implementation Phase | 2024-04-13 | 2024-06-30 | 89 | 30 | Team Members
Review & Final Adjustments | 2024-07-01 | 2024-07-10 | 10 | 55 | Sarah Johnson