## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status | Dependencies | Progress (%)
Create Personal Goals for the Year | 2024-01-01 | 2024-01-15 | 15 | John Doe | High | Completed |  | 100%
Establish Morning Routine | 2024-01-16 | 2024-03-31 | 75 | Medium | High | In Progress | Depends on Goal Setup | 60%
Organize Digital Files | 2024-02-01 | 2024-03-15 | 55 | Sarah Lee | Medium | Not Started |  | 0%
Schedule Weekly Check-Ins | 2024-03-01 | 2024-12-31 | 365 | David Kim | Low | Planned |  | 0%
Review and Adjust Goals Quarterly | 2024-04-15 | 2024-04-30 | 15 | John Doe | High | Not Started | Depends on Morning Routine Completion | 0%
Plan Monthly Budget | 2024-05-01 | 2024-05-31 | 30 | Sarah Lee | Medium | Not Started |  | 0%