## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Progress (%)
Create Personal Goal List | 2024-03-01 | 2024-03-05 | 5 | John Doe | Completed | None | 100
Organize Digital Files | 2024-03-06 | 2024-03-15 | 10 | Jane Smith | In Progress | Task 1 Completed | 60
Schedule Weekly Routine | 2024-03-16 | 2024-03-25 | 10 | Mike Johnson | Not Started | None | 0
Review and Update Goals Monthly | 2024-04-01 | 2024-04-05 | 5 | John Doe | Planned | Task 2 Completed | 0
Maintain a Personal Journal | 2024-03-01 | 2024-12-31 | 365 | All Members | Ongoing | None | 30