## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | Sarah Johnson | Completed
Market Research & Analysis | 2024-01-16 | 2024-02-15 | 30 days | David Kim | In Progress
Strategy Development | 2024-02-16 | 2024-03-31 | 56 days | Lisa Chen | Planned
Design & Prototyping | 2024-04-01 | 2024-05-15 | 65 days | Michael Reed | Not Started
Development Phase | 2024-05-16 | 2024-07-31 | 96 days | Team A (Dev) | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-09-15 | 65 days | Emily Wong | Not Started
Deployment & Launch | 2024-09-16 | 2024-10-31 | 56 days | All Team Members | Not Started
Post-Launch Review & Feedback | 2024-11-01 | 2024-11-30 | 30 days | Sarah Johnson & David Kim | Planned