## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Planning | 2024-03-01 | 2024-03-15 | 15 | John Doe | In Progress
Market Research | 2024-03-16 | 2024-04-05 | 21 | Jane Smith | Not Started
Design Phase | 2024-04-06 | 2024-05-15 | 41 | Alex Chen | Planned
Development Phase | 2024-05-16 | 2024-07-31 | 76 | Team A | Not Started
Testing & Quality Check | 2024-08-01 | 2024-08-31 | 31 | Sarah Lee | Scheduled
Launch & Rollout | 2024-09-01 | 2024-09-15 | 15 | Marketing Team | Not Started