## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Business Plan Development | 2024-03-15 | 2024-03-25 | 10 | Sarah Johnson | In Progress
Market Research & Analysis | 2024-03-26 | 2024-04-10 | 15 | Mike Chen | Pending
Product Line Selection | 2024-04-11 | 2024-04-25 | 15 | Lisa Torres | Not Started
Website & Branding Design | 2024-04-26 | 2024-05-15 | 20 | David Kim | Planned
Secure Funding & Investment Pitch | 2024-05-16 | 2024-06-03 | 18 | Rachel Patel | Scheduled
Launch Preparation & Training | 2024-06-04 | 2024-06-30 | 27 | Team Leadership Group | Not Started