## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Team Leadership | Completed
Needs Assessment & Research | 2024-03-02 | 2024-03-15 | 14 | Research Team | In Progress
Task Planning & Workflow Design | 2024-03-16 | 2024-03-25 | 10 | Project Management Team | Planned
Team Training & Onboarding | 2024-03-26 | 2024-03-31 | 6 | All Team Members | Completed
Final Review & Approval Cycle | 2024-04-01 | 2024-04-10 | 10 | Quality Assurance Team | Pending