## Worksheet
Task | Description | Owner | Start Date | End Date | Status | Priority | Notes
Project Initiation | Define project goals, scope, and key stakeholders. | John Doe | 2024-03-15 | 2024-03-20 | In Progress | High
Requirements Gathering | Collect and document user needs and system requirements. | Jane Smith | 2024-03-21 | 2024-04-05 | Not Started | High
Project Planning | Create detailed project schedule and resource plan. | Alex Chen | 2024-04-06 | 2024-04-15 | Not Started | Medium
Design Phase | Develop wireframes, UI mockups, and process flows. | Maria Garcia | 2024-04-16 | 2024-05-10 | Not Started | Medium
Development Phase | Build the core features and functionality. | David Kim | 2024-05-11 | 2024-07-15 | Not Started | High
Testing & QA | Conduct unit, integration, and user acceptance testing. | Lisa Wong | 2024-07-16 | 2024-08-05 | Not Started | High
Deployment & Launch | Release the project to production and notify stakeholders. | Sam Taylor | 2024-08-06 | 2024-08-10 | Not Started | Medium
Post-Launch Review | Evaluate outcomes, gather feedback, and document lessons learned. | All Team | 2024-08-11 | 2024-08-15 | Not Started | Low