## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
Define Project Scope | John Doe | 2024-03-01 | 2024-03-10 | In Progress | High | None | Clarify objectives and deliverables with stakeholders.
Create Project Timeline | Jane Smith | <2024-03-11 | 2024-03-20 | Not Started | Medium | Scope Definition Complete | Include milestones and review meetings.
Identify Team Members | Alex Turner | 2024-03-15 | 2024-03-18 | Not Started | Medium | Timeline Approved | Assign roles based on skill sets.
Conduct Stakeholder Meeting | Sarah Lee | 2024-03-21 | 2024-03-25 | Planned | High | Team Members Identified | Gather feedback on initial plan.
Finalize Project Budget | Michael Brown | 2024-03-26 | 2024-03-31 | Not Started | High | Stakeholder Meeting Completed | Ensure alignment with personal goals.