## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Research Freelance Market Trends | Alex Johnson | 2024-03-01 | 2024-03-15 | In Progress | High | Gather data from industry reports and forums.
Create Personal Branding Assets | Samantha Lee | 2024-03-16 | 2024-04-05 | Pending | High | Design portfolio, resume, and LinkedIn profile.
Set Up Freelance Platforms | Marcus Chen | 2024-04-06 | 2024-04-15 | Not Started | Medium | Register on Upwork, Fiverr, and Toptal.
Schedule First Client Introductions | Emily Davis | 2024-04-16 | 2024-05-01 | Planned | Medium | Reach out to 5 potential clients via email.
Review Monthly Income & Expenses | Team Lead | 2024-05-02 | 2024-05-31 | Not Started | Low | Analyze financial performance and adjust goals.