## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Progress (%)
Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | Completed | High | 100%
Define Objectives & Goals | Mark Johnson | 2024-03-16 | 2024-03-20 | In Progress | High | 75%
Create Project Timeline | Lisa Chen | 2024-03-21 | 2024-03-25 | Not Started | Medium | 0%
Team Training & Onboarding | David Brown | 2024-03-26 | 2024-03-31 | Planned | Medium | 0%
Weekly Progress Review | All Team Members | 2024-04-01 | Ongoing | Ongoing | Medium | -