## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Define Project Scope | Alex Johnson | 2024-03-15 | 2024-03-20 | In Progress | High | Clarify goals, deliverables, and stakeholders.
Create Project Plan | Sam Rivera | <+td style="text-align: center;">2024-03-212024-03-25 | Not Started | High | Include milestones, timelines, and resource allocation.
Team Kickoff Meeting | Jordan Lee | 2024-03-26 | 2024-03-26 | Not Started | Medium | Introduce project goals and team roles.
Develop Work Breakdown Structure | Mia Chen | 2024-03-27 | 2024-04-01 | Not Started | Medium | Break down tasks into manageable components.
Review and Finalize Plan | Team Lead | 2024-04-02 | 2024-04-03 | Not Started | High | Obtain final approval from stakeholders.