## Worksheet
Task | Assigned To | Due Date | Status | Priority | Progress (%) | Notes
Project Planning | John Doe | 2024-03-15 | In Progress | High | 60% | Finalize scope and timeline.
Market Research | Jane Smith | 2024-03-20 | Not Started | Medium | 0% | Collect data from 5 target groups.
Design Phase | Alex Lee | 2024-04-10 | Scheduled | High | 25% | Draft wireframes and user flows.
Development | Team A | 2024-05-01 | Not Started | High | 0% | Build front-end and back-end modules.
Testing & QA | Sarah Kim | 2024-05-15 | Not Started | Medium | 0% | Conduct functional and security testing.
Launch & Review | All Team | 2024-06-01 | Not Started | Low | 0% | Monitor performance and gather feedback.