## Worksheet
Task | Start Date | End Date | Assigned To | Priority | Status | Progress (%) | Dependencies | Notes
Project Planning Phase | 2024-03-01 | 2024-03-15 | John Doe | High | In Progress | 60% | None | Initial scope and goals defined.
Resource Allocation | 2024-03-16 | 2024-03-25 | Jane Smith | Medium | Not Started | 0% | Project Planning Phase complete | Assign team members and tools.
Design & Strategy Development | 2024-03-26 | 2024-04-10 | Alex Johnson | High | Planned | 0% | Resource Allocation complete | Create visual concepts and user flows.
Development Phase (Phase 1) | 2024-04-11 | 2024-05-05 | Team A | High | Not Started | 0% | Design & Strategy Development complete | Build core features and backend.
Testing & Quality Assurance | 2024-05-06 | 2024-05-30 | Sarah Lee | Medium | Not Started | 0% | Development Phase (Phase 1) complete | Identify bugs and optimize performance.
Final Review & Deployment | 2024-06-01 | 2024-06-15 | John Doe & Jane Smith | High | Not Started | 0% | Testing & QA complete | Final approval and public launch.