## Worksheet
Task Name | Start Date | End Date | Responsibility | Status | Priority | Milestones | Dependencies | Notes / Description
Project Planning Phase | 2024-04-01 | 2024-04-15 | John Doe | In Progress | High | Finalize goals, scope, timeline |  | Define objectives and deliverables for the personal organization system.
Create Daily Routine Framework | 2024-04-16 | 2024-05-10 | Jane Smith | On Track | Medium | Set morning and evening rituals | Project Planning Phase completed | Develop habits to improve focus and reduce procrastination.
Organize Digital Files | 2024-05-11 | 2024-06-30 | Mike Johnson | Not Started | High | Complete file categorization by project type | Daily Routine Framework finalized | Sort emails, documents, photos using consistent naming and folder structure.
Schedule Weekly Reviews | 2024-07-01 | 2024-12-31 | Sarah Lee | Planned | Medium | Monthly progress check-in meetings | Digital Files organized | Evaluate achievements and adjust goals every month.
Personal Goal Setting (Annual) | 2024-10-01 | 2024-10-31 | John Doe | Scheduled | High | Set SMART goals for 2025 | Weekly Reviews in progress | Establish measurable objectives aligned with long-term vision.