## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority | Progress (%) | Milestones | Dependencies | Notes
Project Planning Phase | 2024-03-01 | 2024-03-15 | Sarah Johnson | Completed | High | 100% | Initial scope defined | None
Market Research | 2024-03-16 | 2024-04-10 | Michael Chen | In Progress | Medium | 65% | Survey results collected | Project Planning Phase | Need to finalize target audience data.
Design Development | 2024-04-11 | 2024-05-30 | Emily Rodriguez | Not Started | High | 0% | Wireframes approved | Market Research Complete
Development Phase | 2024-06-01 | 2024-08-15 | David Kim | Not Started | High | 0% | Alpha version ready | Design Development Complete
Testing & Quality Assurance | 2024-08-16 | 2024-09-10 | Lisa Wang | Not Started | Medium | 0% | Bug reports logged | Development Phase Complete
Launch & Training | 2024-09-11 | 2024-10-31 | Team Leadership Committee | Not Started | High | 0% | User onboarding process ready | Testing & QA Complete