## Worksheet
Project Phase | Start Date | End Date | Budget (USD) | Allocated Funds | Remaining Balance | Status | Owner
Planning & Strategy | 2024-01-15 | 2024-02-14 | $15,000 | $13,250 | $1,750 | On Track | Sarah Thompson
Resource Acquisition | 2024-02-15 | 2024-03-31 | $25,000 | $21,800 | $3,200 | On Track | James Rivera
Execution & Development | 2024-04-01 | 2024-07-30 | $75,000 | $58,950 | $16,050 | In Progress | Lisa Chen
Review & Adjustment | 2024-08-01 | 2024-09-30 | $10,000 | $8,500 | $1,500 | Planned | Michael Torres
Final Evaluation & Closure | 2024-10-01 | 2024-10-31 | $5,000 | $4,950 | $50 | Pending | Anna Patel