## Worksheet
Task | Start Date | End Date | Assigned To | Status | Priority | Progress (%)
Define Project Goals | 2024-04-01 | 2024-04-05 | John Doe | Completed | High | 100%
Create Project Timeline | 2024-04-06 | 2024-04-10 | Jane Smith | In Progress | Medium | 65%
Finalize Budget Plan | 2024-04-11 | 2024-04-15 | Mike Johnson | Pending | Low | 0%
Schedule Team Meetings | 2024-04-16 | 2024-04-20 | Sarah Lee | Planned | Medium | 0%
Review and Adjust Plan | 2024-04-21 | 2024-04-25 | All Team Members | Pending | High | 0%