## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority
Define Project Scope | 2024-03-01 | 2024-03-07 | John Doe | In Progress | High
Create Project Plan | 2024-03-08 | 2024-03-15 | Jane Smith | Not Started | High
Conduct Stakeholder Interviews | 2024-03-16 | 2024-03-22 | Alex Brown | Not Started | Medium
Finalize Requirements Document | 2024-03-23 | 2024-03-30 | Sarah Lee | Not Started | High
Review and Approve Project Plan | 2024-04-01 | 2024-04-05 | Project Manager | Not Started | Critical
Template Version 1.0 - Personal Organization Project Timeline