## Worksheet
Project Name | Start Date | Due Date | Status | Priority | Assigned To | Progress (%) | Notes
Website Redesign | 2024-03-01 | 2024-05-30 | In Progress | High | John Doe | 65% | Design mockups approved; development in progress.
Monthly Reporting System | 2024-02-15 | 2024-04-30 | Completed | Medium | Jane Smith | 100% | Reports now available in dashboard.
Team Training Sessions | 2024-03-10 | 2024-04-15 | Pending Start | High | Alex Brown | 0% | Schedule confirmed; waiting for participant sign-up.
Office Workspace Update | 2024-04-01 | 2024-06-30 | Not Started | Low | Sarah Lee | 0% | Needs budget approval; initial survey sent.