## Worksheet
Project Name | Start Date | End Date | Current Status | Owner | Priority Level | Progress (%) | Next Milestone | Notes
Website Redesign | 2024-03-15 | 2024-06-30 | In Progress | Sarah Johnson | High | 65% | UI Mockups Finalized (April 10) | Design feedback from stakeholders pending.
Client Onboarding Process | 2024-04-01 | 2024-05-31 | On Track | Michael Chen | Medium | 90% | Training Module Launch (May 20) | All client training materials approved.
Team Retreat Planning | 2024-05-10 | 2024-06-15 | Pending Start | Lisa Rodriguez | High | 20% | Final location and date confirmation (May 30) | Budget review scheduled for May 18.
CRM System Integration | 2024-03-20 | 2024-07-15 | Delayed | David Kim | Critical | 40% | API Testing Phase (June 10) | Vendor delay in data export format.