## Worksheet
Process Documentation
Business Plan - Client View
Process Step | Description | Responsible Team/Person | Duration (Days) | Status
Initiation & Planning | Define scope, objectives, and key deliverables of the project. | Project Manager | 5 | In Progress
Requirement Gathering | Capture business needs through client meetings and surveys. | Business Analyst | 7 | Pending Approval
Design & Prototyping | Create wireframes, UI mockups, and technical architecture. | UX Designer & Developer Lead | 10 | Pending Review
Development Phase 1 | Implement core system modules based on design specifications. | Software Development Team | 14 | In Progress
Testing & QA | Conduct unit, integration, and user acceptance testing. | QA Team & Client Representative | 7 | Pending Start
Deployment Planning | Prepare go-live strategy, data migration, and rollback plans. | IT Operations & Project Manager | 5 | Pending Start
Go-Live & Launch | Deploy system to production environment and initiate operations. | Deployment Team & Client Support | 3 | Pending Start
Post-Implementation Review | Evaluate project outcomes against KPIs and document lessons learned. | Project Manager & Stakeholders | 5 | Pending Start