## Worksheet
Business Plan - Process Documentation
Process Step | Description | Responsible Role | Tools/Systems Used | Status (Initiated/In Progress/Completed) | Notes & Dependencies
1. Business Development & Market Analysis
1.1 Market Research | Collect and analyze industry trends, customer needs, and competitor landscape. | Market Analyst | Salesforce, SEMrush, Google Trends | In Progress | Requires quarterly updates post-launch.
1.2 Target Audience Segmentation | Define and categorize customer segments based on behavior and demographics. | Marketing Manager | Mixpanel, CRM Database | Completed | Data validated through survey feedback.
2. Product Development & Design
2.1 Concept Validation | Test product ideas with focus groups and MVP prototypes. | Product Owner | Figma, Google Forms, Miro | Completed | MVP received 87% positive feedback from users.
2.2 Design & Prototyping | Create detailed wireframes and interactive prototypes. | UX Designer | Figma, Adobe XD | In Progress | Final review scheduled for next Monday.
3. Operations & Strategic Planning
3.1 Supply Chain Setup | Identify and onboard suppliers, establish logistics flow. | Procurement Manager | SAP Ariba, EDI Systems | Initiated | Negotiations with 3 vendors underway.
3.2 Hiring Plan & Team Structure | Create org chart and job descriptions for core departments. | HR Director | Workday, LinkedIn Recruiter | In ProgressNext steps: Finalize job posts by Friday.
4. Financial Planning & Funding
4.1 Revenue Model Development | Define pricing strategy and revenue streams (subscriptions, one-time sales). | Finance Lead | Excel, QuickBooks Pro | CompletedModel approved by board.
4.2 Funding Strategy & Investor Pitch | Prepare funding request and pitch deck for seed round. | CFO, CEO | Pitch Deck (PowerPoint), CapTable Software | In ProgressTarget close date: Q3 2024.
5. Go-to-Market & Post-Launch Support
5.1 Marketing Campaign Plan | Develop digital and traditional marketing strategy. | Marketing Director | Hootsuite, Mailchimp, Google Ads | In ProgressA/B testing underway.
5.2 Customer Support Infrastructure | Set up helpdesk, SLAs, and training for support staff. | Customer Success Manager | Zendesk, Notion Knowledge Base | InitiatedTraining sessions scheduled for week of May 13.