## Worksheet
Freelancer Business Plan - Process Documentation
Project Name | Client Website Redesign & Development
Freelancer Name | Jane Doe, Senior Web Developer
Date Created | May 5, 2024
Status | In Progress
Phase | Description | Deliverables | Timeline (Days) | Owner
Phase 1: Discovery & Planning | Analyze client requirements, goals, and target audience. Define project scope and key objectives. | Project Brief Document, Stakeholder Interview Summary | 5 | Jane Doe
Phase 2: Design & Wireframing | Create wireframes, UI mockups, and design prototypes based on client feedback. | High-Fidelity Mockups, Interactive Prototype (Figma) | 7 | Jane Doe
Phase 3: Development | Frontend and backend implementation using React, Node.js, and PostgreSQL. | Functional Website Codebase, Responsive Layouts | 15 | Jane Doe
Phase 4: Testing & QA | Conduct cross-browser testing, performance checks, and usability validation. | Test Reports, Bug Fix Log | 5 | Jane Doe
Phase 5: Deployment & Handover | Deploy to production server, transfer documentation, and provide training. | Live Website, User Manual, Training Session Recordings | 3 | Jane Doe
Total Duration | 35 days (approx. 5 weeks)