## Worksheet
Monthly Business Plan - Process Documentation
Month & Year | Objective/Goal | Key Activities | Status (Progress %) | Budget Allocated ($) | Budget Spent ($) | Remarks / Notes
January 2024 | Increase customer acquisition by 15% | Launch digital marketing campaign, optimize website conversion rate | 78% | 15,000 | 11,250 | Campaign performance exceeds targets; adjust budget allocation for February.
February 2024 | Improve product quality feedback loop | Implement customer survey system, analyze feedback weekly | 55% | 8,000 | 4,400 | Survey platform integrated; data collection ongoing.
March 2024 | Expand to two new markets | Market research, legal compliance check, partner onboarding | 30% | 50,000 | 15,875 | Midway through research phase; delays due to regulatory review.
April 2024 | Optimize internal workflow efficiency | Implement new task management system, staff training sessions | 90% | 12,500 | 11,750 | All teams onboarded; initial feedback positive.
May 2024 | Launch new product line (Phase 1) | Design finalization, prototype testing, team training | 65% | 35,000 | 22,750 | Testing phase completed; full launch planned for June.
This document is intended for internal process documentation and strategic planning purposes. Updated monthly.