## Worksheet
Process ID | Process Name | Description | Responsible Team/Person | Status | Start Date | Target Completion Date | Actual Completion Date | Status Update (Last Week)
P001 | Market Research & Analysis | Conduct market analysis to identify trends and customer needs. | Marketing Team | In Progress | 2024-01-15 | 2024-03-31 | - | Completed 60% of surveys; data collection ongoing.
P002 | Product Development Phase 1 | Design and prototype development for new product line. | R&D Department | Planning | 2024-02-01 | 2024-05-15 | - | Initial design concept approved; resource allocation pending.
P003 | Financial Forecasting & Budgeting | Create detailed financial models and budget allocations. | Finance Team | In Review | 2024-01-20 | 2024-03-15 | - | Budget draft submitted for management review.
P004 | Legal Compliance Check | Ensure all business processes comply with regional regulations. | Legal Department | Completed | 2023-12-15 | 2024-01-31 | 2024-01-30 | All compliance checks passed. Certificate issued.