## Worksheet
WEEKLY PROCESS DOCUMENTATION - BUSINESS PLAN
Week of | Objective / Goal | Key Activities & Tasks | Status (Completed/In Progress/Pending) | Responsible Person(s) | Notes / Comments
Week 1: January 1 - January 7, 2024
Jan 1, 2024 | Finalize business model canvas | Review and update key components: value proposition, customer segments, revenue streams | In Progress | Jane Doe | Needs input from marketing team by Jan 3rd.
Week 2: January 8 - January 14, 2024
Jan 8, 2024 | Conduct market research & competitor analysis | Collect data on top five competitors; analyze pricing and customer reviews. | Completed | John Smith | Data compiled into shared drive. Report ready for review.
Week 3: January 15 - January 21, 2024
Jan 15, 2024 | Develop financial projections (Year 1) | Create detailed income statement, cash flow forecast, and balance sheet. | Pending | Lisa Chen | Finance team meeting scheduled for Jan 17th to align assumptions.
Week 4: January 22 - January 28, 2024
Jan 23, 2024 | Finalize go-to-market strategy | Define channels, customer acquisition plan, and launch timeline. | In Progress | Alex Johnson | Present draft to executives on Jan 25th.
Weekly Summary & Next Steps (End of Week 4)
This week, we completed market research and are progressing on the financials. Key focus next week: finalize business model, review all components for alignment, and prepare presentation deck for stakeholders.