## CRM Tracker - Quarterly
Quarter | CRM System Version | Key Activities / Milestones | Status | Responsible Team/Person | Dates (Start - End) | Notes/Comments
Q1 2024 | v3.1.5 | CRM Migration from Legacy System | Completed | IT & Sales Ops | Jan 05 - Mar 31, 2024 | Data validation completed; no critical issues found.
Q1 2024 | v3.1.5 | User Training Sessions (All Departments) | Completed | Training Team | Feb 01 - Feb 28, 2024 | 95% attendance; feedback form collected.
Q2 2024 | v3.1.5 | Integration with Marketing Automation Tool | In Progress | IT & Marketing | Apr 01 - Jun 30, 2024 | API connection established; testing underway.
Q2 2024 | v3.1.5 | CRM Performance Optimization Review | Pending | IT Support | May 15 - May 30, 2024 | Scheduled for next week.
Q3 2024 | v3.2.0 (Planned) | Feature Enhancement: Custom Dashboards | Not Started | Product Team | Jul 01 - Sep 30, 2024 | Requirements gathering in progress.
Q3 2024 | v3.2.0 (Planned) | Quarterly CRM Audit & Data Cleansing | Not Started | Data Governance Team | Aug 15 - Aug 31, 2024 | Cleanse duplicates and outdated records.