## Worksheet
Finance Planning View - Process Documentation
Process Step | Description | Owner | Start Date | End Date | Status | Budget Allocated (USD)
Annual Budget Forecasting | Develop preliminary financial forecasts for the fiscal year based on historical data and market trends. | Finance Manager | 2024-01-05 | 2024-01-31 | In Progress | $85,000.00
Departmental Budget Submission | Collect budget requests from all departments with supporting documentation. | Finance Analysts | 2024-02-01 | 2024-03-15 | Pending | $185,675.33
Budget Review & Approval (Stage 1) | Review submitted budgets for feasibility and alignment with strategic goals. | Executive Finance Committee | 2024-03-16 | 2024-03-31 | Pending | $89,550.75
Budget Adjustment & Finalization | Adjust allocations based on feedback and finalize the approved budget. | Finance Director | 2024-04-01 | 2024-05-15 | Pending | $37,891.67
Budget Distribution & Communication | Share finalized budget with all stakeholders and initiate tracking mechanisms. | Finance Communications Team | 2024-05-16 | 2024-05-31 | Pending | $18,975.33
Monthly Financial Review Meetings | Conduct monthly reviews of actual spending against budget. | All Department Heads & Finance | 2024-06-01 | Ongoing (until 2025-12-31) | Pending | $98,745.88
Year-End Financial Reporting | Compile and publish comprehensive financial results for the fiscal year. | Chief Financial Officer | 2025-01-01 | 2025-03-31 | Pending | $67,458.99