## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Initiate Project | 2023-10-01 | 2023-10-05 | 5 | In Progress
Requirements Gathering | 2023-10-06 | 2023-10-15 | 10 | In Progress
Design Phase | 2023-10-16 | 2023-10-30 | 15 | Pending
Development Phase | 2023-10-31 | 2023-12-15 | 45 | Pending
Testing Phase | 2023-12-16 | 2024-01-15 | 31 | Pending
Deployment | 2024-01-16 | 2024-01-31 | 16 | Pending
Post-Implementation Review | 2024-02-01 | 2024-02-15 | 15 | Pending