## Worksheet
Process Documentation - Gantt Chart (Business Use)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Requirements Gathering
REQ-01 | Define Project Scope | 2024-04-01 | 2024-04-05 | 5 | In Progress
REQ-02 | Stakeholder Interviews | 2024-04-03 | 2024-04-15 | 13 | In Progress
Phase 2: Design & Planning
DES-01 | Create Process Flow Diagrams | 2024-04-16 | 2024-04-30 | 15 | Pending
DES-02 | Finalize Process Documentation | 2024-05-15 | 2024-05-15 | 1 | Milestone
Phase 3: Implementation
IMP-01 | Develop Documentation Templates | 2024-05-16 | 2024-05-31 | 16 | In Progress
Phase 4: Review & Approval
REV-01 | Internal Peer Review | 2024-06-01 | 2024-06-15 | 15 | Pending
Phase 5: Finalization
FNL-01 | Final Document Submission | 2024-06-16 | 2024-06-30 | 15 | Pending
Total Duration: |  |  |  | 64 Days