## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Status
Requirement Gathering | 2023-10-01 | 2023-10-05 | 5 | 100 | Completed
Design Phase | 2023-10-06 | 2023-10-15 | 10 | 85 | In Progress
Development - Module A | 2023-10-16 | 2023-10-30 | 15 | 45 | In Progress
Development - Module B | 2023-11-01 | 2023-11-15 | 15 | 0 | Not Started
Testing Phase (UAT) | 2023-11-16 | 2023-11-30 | 15 | 0 | Not Started
Documentation Finalization | 2023-12-01 | 2023-12-05 | 5 | 0 | Not Started
Total Duration: |  |  |  | 60 Days