## Worksheet
Process Documentation - Gantt Chart Dashboard
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%)
T001 | Requirement Gathering | John Doe | 2024-06-15 | 2024-07-15 | Active
T002 | Design Phase | Jane Smith | 2024-07-16 | 2024-08-15 | Active
T003 | Development | Mike Johnson | 2024-08-16 | 2024-10-15 | Active
T004 | Testing & QA | Sarah Brown | 2024-10-16 | 2024-11-30 | Completed
T005 | Documentation Finalization | Tom Wilson | 2024-11-30 | 2024-12-15 | Active
T006 | Deployment | Lisa Park | 2024-12-15 | 2024-12-30 | Active
Total Duration | [5 empty] | 2024-06-15 to 2024-12-30 (6.5 months)