## Worksheet
Process Documentation - Detailed Gantt Chart
Task ID | Task Description | Start Date | End Date | Duration (Days) | Progress
Phase 1: Project Planning
PLN-001 | Define project scope and objectives | 2024-04-01 | 2024-04-05 | 5
PLN-002 | Identify stakeholders and requirements | 2024-04-03 | 2024-04-15 | 13
PLN-M01 | Project Charter Approved | 2024-04-15 | 2024-04-15 | 1
Phase 2: System Design
DES-001 | Develop system architecture diagram | 2024-04-16 | 2024-04-25 | 10
DES-002 | Create database schema and data flow diagrams | 2024-04-18 | 2024-05-15 | 35
DES-M01 | Design Phase Complete - Review & Sign-off | 2024-05-17 | 2024-05-17 | 1
Phase 3: Application Development
DEV-001 | Frontend UI/UX Implementation (Module A) | 2024-05-18 | 2024-06-30 | 45
DEV-002 | Backend API Development (Module B) | 2024-05-18 | 2024-07-15 | 69
DEV-003 | Database Integration and Optimization | 2024-06-15 | 2024-07-15 | 31
Phase 4: Quality Assurance & Testing
TEST-001 | Unit Testing (All Components) | 2024-07-16 | 2024-08-15 | 31
TEST-002 | Integration Testing (End-to-End) | 2024-08-16 | 2024-08-31 | 16
TEST-003 | User Acceptance Testing (UAT) | 2024-09-01 | 2024-10-15 | 45
Phase 5: Deployment & Go-Live
DEP-001 | Final System Configuration and Security Review | 2024-10-16 | 2024-11-30 | 45
DEP-M01 | Production Deployment (Go-Live) | 2024-12-01 | 2024-12-01 | 1
Phase 6: Post-Implementation Support
POST-001 | First 30-Day Performance Monitoring & Optimization | 2024-12-02 | 2025-01-31 | 61
POST-002 | Final Project Review and Documentation Sign-off | 2025-01-31 | 2025-01-31 | 1
This document is a detailed Gantt chart representation of the process documentation timeline. Updated on: