## Employee View - Gantt Chart
Employee View - Process Documentation Gantt Chart
Task / Activity | Start Date | End Date | Duration (Days) | Progress (%) | Status
Define Process Scope | 2024-04-01 | 2024-04-05 | 5 |  | In Progress
Interview Stakeholders | 2024-04-06 | 2024-04-15 | 10 |  | In Progress
Document Current Workflow | 2024-04-16 | 2024-04-30 | 15 |  | In Progress
Identify Bottlenecks | 2024-05-01 | 2024-05-10 | 10 |  | Pending
Design Improved Process | 2024-05-11 | 2024-05-31 | 21 |  | Not Started
Review with Team Leads | 2024-06-01 | 2024-06-15 | 15 |  | Not Started
Finalize Documentation | 2024-06-16 | 2024-06-30 | 15 |  | Not Started
Process Approval (Milestone) | 2024-07-01 | 2024-07-01 | 1 |  | Not Started
Train Team on New Process | 2024-07-02 | 2024-07-15 | 14 |  | Not Started
Go-Live and Monitor | 2024-07-16 | 2024-07-31 | 16 |  | Not Started
Total Duration: |  |  | 142 days
Note: This Gantt chart is designed for employee view. All dates are in YYYY-MM-DD format. Progress percentages reflect estimated completion based on current status.