## Worksheet
Process Documentation Gantt Chart (Extended)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress Timeline (Calendar View)
[5 empty] | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12
|  |  |  | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2
PH1-001 | Project Initiation | 2024-01-01 | 2024-01-15 | 15 | In Progress
PH1-002 | Requirements Collection | 2024-01-16 | 2024-01-31 | 16 | In Progress
PH1-003 | System Design & Documentation | 2024-02-01 | 2024-03-15 | 45 | Not Started
MS-01 | Design Approval (Milestone) | 2024-03-15 | 2024-03-15 | 1 | Milestone Reached | ★
PH2-001 | Development Phase I | 2024-03-18 | 2024-04-15 | 30 | In Progress
PH2-002 | Unit & Integration Testing | 2024-04-16 | 2024-05-15 | 31 | Not Started
MS-02 | Final Acceptance & Sign-off | 2024-05-16 | 2024-05-17 | 1 | Pending | ★
Total Duration: |  |  |  |  | 120 Days