## Worksheet
Process Documentation - Financial View Gantt Chart
Task ID | Task Name | Start Date | End Date | Budget Allocation ($) | Status | Progress (%)
T001 | Project Initiation | 2024-01-15 | 2024-01-31 | $7,500 | In Progress
T002 | Requirement Analysis | 2024-02-01 | 2024-02-15 | $15,000 | In Progress
T003 | Design Phase | 2024-02-16 | 2024-03-15 | $35,000 | Not Started
T004 | Development Phase | 2024-03-16 | 2024-05-31 | $85,000 | Not Started
T005 | Testing & QA | 2024-06-01 | 2024-06-30 | $35,000 | Not Started
T006 | Deployment & Training | 2024-07-01 | 2024-07-31 | $55,000 | Not Started
T007 | Post-Implementation Review | 2024-08-01 | 2024-08-15 | $15,000 | Not Started
Total: | $247,500 |  |  |  | Summary