## Worksheet
Process Documentation - Freelancer Gantt Chart
Task ID | Task Description | Start Date | End Date | Status | Progress (%)
T001 | Requirements Gathering & Analysis | 2023-10-01 | 2023-10-15 | In Progress | 75%
T002 | Process Design & Flowcharting | 2023-10-16 | 2023-11-05 | In Progress | 40%
T003 | Documentation Drafting | 2023-11-06 | 2023-11-25 | Delayed | 20%
T004 | Review & Feedback Integration | 2023-11-26 | 2023-12-10 | In Progress | 65%
T005 | Final Documentation & Approval | 2023-12-11 | 2023-12-25 | Completed | 100%
T006 | Knowledge Transfer Session | 2023-12-26 | 2024-01-05 | In Progress | 35%
T007 | Documentation Archive & Sharing | 2024-01-06 | 2024-01-15 | Delayed | 10%
T008 | Post-Process Review & Reporting | 2024-01-16 | 2024-01-31 | In Progress | 55%
Legend
Completed– Task has been fully completed.
In Progress– Task is currently being worked on.
Delayed– Task is behind schedule.