## Worksheet
Process Documentation - Gantt Chart (One Page)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
1 | Project Initiation | 2024-04-01 | 2024-04-05 | 5 | In Progress | 65%
1.1 | Stakeholder Identification | 2024-04-01 | 2024-04-03 | 3 | In Progress | 85%
1.2 | Requirements Gathering | 2024-04-03 | 2024-04-15 | 13 | 75%
2 | Process Design & Analysis | 2024-04-16 | 2024-05-15 | 30 | 58%
2.1 | Current State Mapping | 2024-04-16 | 2024-05-03 | 18 | 95%
2.2 | Future State Modeling | 2024-05-06 | 2024-05-15 | 10 | 38%
3 | Documentation Development | 2024-05-16 | 2024-06-15 | 31
3.1 | Process Flow Diagrams | 2024-05-16 | 2024-06-05 | 21
3.2 | Standard Operating Procedures (SOPs) | 2024-06-06 | 2024-06-15 | 11
MILESTONE: Project Review & Approval (June 25, 2024)