## Worksheet
Process Documentation - Gantt Chart (Personal Use)
Task ID | Task Description | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation & Planning | 2025-04-01 | 2025-04-15 | In Progress
T002 | Requirements Gathering | 2025-04-16 | 2025-04-30 | In Progress
T003 | Design Phase | 2025-05-01 | 2025-05-14 | Not Started
T004 | Development Sprint 1 | 2025-05-15 | 2025-06-14 | Not Started
T005 | Testing & QA | 2025-06-15 | 2025-07-14 | Not Started
T006 | Deployment & Training | 2025-07-15 | 2025-07-31 | Not Started
MS01 | Project Kickoff | 2025-04-01 | 2025-04-01 | Milestone Reached
MS02 | Final Delivery | 2025-07-31 | 2025-07-31 | Milestone Pending
This Gantt chart is for personal use and documentation purposes. Last updated: 2025-04-01.