## Worksheet
Process Documentation Gantt Chart
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
P1-001 | Requirements Gathering | 2023-10-02 | 2023-10-15 | Completed
P1-002 | Design Specification | 2023-10-16 | 2023-10-31 | In Progress
P1-003 | Process Development | 2023-11-01 | 2023-11-25 | Not Started
P1-004 | Testing & QA | 2023-11-26 | 2023-12-15 | Not Started
P1-005 | Documentation Finalization | 2023-12-16 | 2023-12-31 | Not Started
MS-01 | Milestone: Phase 1 Complete | 2023-10-15 | 2023-10-15 | Completed