## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | 2023-10-01 | 2023-10-15 | In Progress
T002 | Requirements Gathering | 2023-10-16 | 2023-11-15 | Not Started
T003 | Design Phase | 2023-11-16 | 2024-01-15 | In Progress
T004 | Development | 2024-01-16 | 2024-03-31 | Not Started
T005 | Testing & QA | 2024-04-01 | 2024-05-31 | Not Started
T006 | Deployment | 2024-06-01 | 2024-07-15 | Not Started
M001 | Project Kickoff | 2023-10-01 | 2023-10-01 | Milestone Achieved
M002 | Requirements Finalized | 2023-11-15 | 2023-11-15 | Milestone Achieved
M003 | Design Approved | 2024-01-15 | 2024-01-15 | Milestone Achieved
M004 | Project Complete | 2024-07-15 | 2024-07-15 | Milestone Pending