## Worksheet
Process Documentation - Team Use Gantt Chart
Task ID | Task Name | Responsible Team Member | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | Project Manager | 2023-10-01 | 2023-10-15 | In Progress | 45%
T002 | Requirements Gathering | Business Analyst | 2023-10-16 | 2023-10-31 | In Progress | 75%
T003 | System Design Phase | Lead Developer | 2023-11-01 | 2023-11-25 | To Do | 0%
T004 | Development Sprint 1 | Development Team | 2023-11-26 | 2023-12-15 | To Do | 0%
T005 | Development Sprint 2 | Development Team | 2023-12-16 | 2024-01-05 | To Do | 0%
M01 | Mid-Project Review | Project Manager | 2023-12-15 | 2023-12-17 | Pending
T006 | Testing & QA Phase | QA Team | 2024-01-08 | 2024-01-31 | To Do
T007 | User Training & Documentation | Documentation Specialist | 2024-02-01 | 2024-02-15 | To Do
M02 | Project Delivery & Handover | Project Manager | 2024-02-16 | 2024-02-17 | Pending
Note:This Gantt chart is designed for team use and can be exported to Excel for further analysis.